## 0621
5verflow (Team 5) Project Planning
1. Project Description
Project Name | Secure Face ID
Project Schedule | 2021-05-31 ~ 2021-07-02
Update Date | 2021-06-21
Project Members | Name | Role (Phase 1) |  |  |  | Role (Phase 2)
| SeungWook Cha | Team Lead |  |  |  | Team Lead
| SungJun Lee | Requirement |  |  |  | Doc. Anal.
| DongHyuk Han | Infrastructure |  |  |  | Doc. Anal. & Test
| WooLam Kang | SW Development |  |  |  | Impl. Anal. & Test
| YooKyoung Choi | Requirement |  |  |  | Doc. Anal. & Test
| YoungJinn Lee | System Design |  |  |  | Impl. Anal. & Test
2. Project Schedule Green Box : 1st Planning Red Box : 2nd Planning V : Activity C : complete
Category | Item | Phase 1 | [14 empty] | Phase 2 | [9 empty] | Leading Responsibility | Mandatory /Optional | Output
|  | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02
Project Planning | Project Planning (Phase 1) | [25 empty] | SW Cha | M | (Team 5) Project Planning.xslx | bar: 2021-05-31 to 2021-06-03
| Project Planning (Phase 2) | [25 empty] | SW Cha | M | (Team 5) Project Planning.xslx | bar: 2021-06-21
Funcional Requirement | Function Requirement Analysis | [25 empty] | YJ Lee | M | Preliminary Functional Requirement List | bar: 2021-06-04 to 2021-06-08
| Review | [25 empty] | YK Choi | M | Essential Functional Requirement List | bar: 2021-06-04 to 2021-06-08
Security Requirement | Asset List | [25 empty] | YK Choi | M | Asset List | bar: 2021-06-04 to 2021-06-08
| Threat Modeling | [25 empty] | SJ Lee, YK Choi | M | DFD (.tm file from Microsoft Threat Modeling tool) STRIDE | bar: 2021-06-04 to 2021-06-08
| Risk Assessment | [25 empty] | SW Cha | M | OWASP | bar: 2021-06-04 to 2021-06-08
| Mitigation | [25 empty] | SJ Lee | M | Mitigation Strategies | bar: 2021-06-04 to 2021-06-09
| Review | [25 empty] | All | M | Essential Security Requirement List | bar: 2021-06-07 to 2021-06-10
Development | Client - User interface | [25 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-11
| Client - Security (TLS) | [25 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Server - Main Functionality | [25 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-10
| Server - Security (TLS) | [25 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Server - Secure Storage | [25 empty] | YK Choi | M | Source Codes | bar: 2021-06-11 to 2021-06-17
| Open Source Vulnerability analysis | [25 empty] | DH Han | O | open source vulnerability analysis report
| Static Analysis | [25 empty] | WL Kang | O | static analysis report | bar: 2021-06-11 to 2021-06-17
Testing | Test Case | [25 empty] | YK Choi | M | Test case list | bar: 2021-06-11 to 2021-06-15
| Function Test | [25 empty] | YJ Lee | M | Function Test Case & Report | bar: 2021-06-15 to 2021-06-17
| Security Test | [25 empty] | YJ Lee | M | Security Test Case & Report | bar: 2021-06-16 to 2021-06-17
Documents | Developer Guide | [25 empty] | SJ Lee | M | Developer Artifacts and Documentaion | bar: 2021-06-14 to 2021-06-17
| Presentation | [25 empty] | YJ Lee | M | Phase 1. Presentation | bar: 2021-06-14 to 2021-06-17
Analysis | Requirement Analysis of Team6 | [25 empty] | SJ Lee | - | Brief report for Requirements and considered threats | bar: 2021-06-21 to 2021-06-25
| Implementation Analysis of Team6 | [25 empty] | WL Kang | - | Questions to Team6 (if exist), Analyzed Diagrams | bar: 2021-06-21 to 2021-06-25
| Test Method Analysis | [25 empty] | DH Han | - | List of Test methods | bar: 2021-06-21 to 2021-06-25
| Attack Scenario Listing | [25 empty] | All |  | Attack Scenario List for Team6's artifacts | bar: 2021-06-22 to 2021-06-28
Testing | Given Test Case | [25 empty] | YK Choi | - | Test case result | bar: 2021-06-23 to 2021-06-25
| Attack Scenario Attempt | [25 empty] | All | - | Attack Method & Result Report | bar: 2021-06-23 to 2021-06-30
| Penetration Test | [25 empty] | DH Han | - | Penetrate method and result | bar: 2021-06-25 to 2021-06-30
Results | Test Results Analysis | [25 empty] | YJ Lee | - | Attack Result Analysis | bar: 2021-06-25 to 2021-06-30
| Secure Recommendations | [25 empty] | YJ Lee | - | Recommendations for mitigation Report | bar: 2021-06-28 to 2021-06-30
Documents | Final Report | [25 empty] | SW Cha | M | Final Report for Overall Studio Project | bar: 2021-06-29 to 2021-07-01
| Presentation | [25 empty] | WL Kang | M | Phase 2. Presentation | bar: 2021-06-29 to 2021-07-01
3. Role and Responsibility
Category | Item | 2021-05-31: Responsibility
Presentation | Phase 1 Presentation | 2021-05-31: YJ Lee
| Phase 2 Presentation | 2021-05-31: WL Kang
Phase 1 | Chapter 1. Project Overview | 2021-05-31: SW Cha
| Chapter 2. System Description | 2021-05-31: DH Han
| Chapter 3. Threat Modeling | 2021-05-31: SJ Lee, YK Choi
| Chapter 4. Risk Assessment | 2021-05-31: SW Cha
| Chapter 5. Mitigation | 2021-05-31: SJ Lee
| Chapter 6. Security Requirements | 2021-05-31: YJ Lee
| Chapter 7. Implementation | 2021-05-31: DH Han, WL Kang
Phase 2 | Requirement Analysis | 2021-05-31: SJ Lee, YK Choi
| Implementation analysis | 2021-05-31: WL Kang, SW Cha
| Test Method Analysis | 2021-05-31: DH Han, YJ Lee
| Attack Scenario Listing | 2021-05-31: All
| Given Test Case | 2021-05-31: YK Choi
| Attack Test | 2021-05-31: All
| Penetration Test | 2021-05-31: DH Han
| Result Analysis and Mitation Recomm. | 2021-05-31: YJ Lee

## 0607
5verflow (Team 5) Project Planning
1. Project Description
Project Name | Secure Face ID
Project Schedule | 2021-05-31 ~ 2021-06-18
Update Date | 2021-06-17
Project Members | Name | Role
| SeungWook Cha | Team Lead
| SungJun Lee | Requirement
| DongHyuk Han | Infrastructure
| WooLam Kang | SW Development
| YooKyoung Choi | Requirement
| YoungJinn Lee | System Design
2. Project Schedule Green Box : 1st Planning Red Box : 2nd Planning V : Activity C : complete
Category | Item | Phase 1 | [14 empty] | Phase 2 | [9 empty] | Leading Responsibility | Mandatory /Optional | Output
|  | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18 | 2021-06-21 | 2021-06-22 | 2021-06-23 | 2021-06-24 | 2021-06-25 | 2021-06-28 | 2021-06-29 | 2021-06-30 | 2021-07-01 | 2021-07-02
Project Planning | Project Planning (Phase 1) | [25 empty] | SW Cha | M | (Team 5) Project Planning.xslx | bar: 2021-05-31 to 2021-06-03
| Project Planning (Phase 2) | [25 empty] | SW Cha | M | (Team 5) Project Planning.xslx | bar: 2021-06-21
Funcional Requirement | Function Requirement Analysis | [25 empty] | YJ Lee | M | Preliminary Functional Requirement List | bar: 2021-06-04 to 2021-06-08
| Review | [25 empty] | YK Choi | M | Essential Functional Requirement List | bar: 2021-06-04 to 2021-06-08
Security Requirement | Asset List | [25 empty] | YK Choi | M | Asset List | bar: 2021-06-04 to 2021-06-08
| Threat Modeling | [25 empty] | SJ Lee, YK Choi | M | DFD (.tm file from Microsoft Threat Modeling tool) STRIDE | bar: 2021-06-04 to 2021-06-08
| Risk Assessment | [25 empty] | SW Cha | M | OWASP | bar: 2021-06-04 to 2021-06-08
| Mitigation | [25 empty] | SJ Lee | M | Mitigation Strategies | bar: 2021-06-04 to 2021-06-09
| Review | [25 empty] | All | M | Essential Security Requirement List | bar: 2021-06-07 to 2021-06-10
Development | Client - User interface | [25 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-11
| Client - Security (TLS) | [25 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Server - Main Functionality | [25 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-10
| Server - Security (TLS) | [25 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Server - Secure Storage | [25 empty] | YK Choi | M | Source Codes | bar: 2021-06-11 to 2021-06-17
| Open Source Vulnerability analysis | [25 empty] | DH Han | O | open source vulnerability analysis report
| Static Analysis | [25 empty] | WL Kang | O | static analysis report | bar: 2021-06-11 to 2021-06-17
Testing | Test Case | [25 empty] | YK Choi | M | Test case list | bar: 2021-06-11 to 2021-06-15
| Function Test | [25 empty] | YJ Lee | M | Function Test Case & Report | bar: 2021-06-15 to 2021-06-17
| Security Test | [25 empty] | YJ Lee | M | Security Test Case & Report | bar: 2021-06-16 to 2021-06-17
Documents | Developer Guide | [25 empty] | SJ Lee | M | Developer Artifacts and Documentaion | bar: 2021-06-14 to 2021-06-17
| Presentation | [25 empty] | YJ Lee | M | Phase 1. Presentation | bar: 2021-06-14 to 2021-06-17
3. Role and Responsibility
Category | Item | 2021-05-31: Responsibility
Presentation | Phase 1 Presentation | 2021-05-31: WL Kang
| Phase 2 Presentation | 2021-05-31: YJ Lee
Documentation | Chapter 1. Project Overview | 2021-05-31: SW Cha
| Chapter 2. System Description | 2021-05-31: DH Han
| Chapter 3. Threat Modeling | 2021-05-31: SJ Lee, YK Choi
| Chapter 4. Risk Assessment | 2021-05-31: SW Cha
| Chapter 5. Mitigation | 2021-05-31: SJ Lee
| Chapter 6. Security Requirements | 2021-05-31: YJ Lee
| Chapter 7. Implementation | 2021-05-31: DH Han, WL Kang

## Copy of 0607
5verflow (Team 5) Project Planning
1. Project Description
Project Name | Tartan Secure Camera Application
Project Schedule | 2021-05-31 ~ 2021-06-18
Update Date | 2021-06-07
Project Members | Name | Role
| SeungWook Cha | Team Lead
| SungJun Lee | Requirement
| DongHyuk Han | Infrastructure
| WooLam Kang | SW Development
| YooKyoung Choi | Requirement
| YoungJinn Lee | System Design
2. Project Schedule
Category | Item | Due date (KST) | [14 empty] | Leading Responsibility | Mandatory /Optional | Output
|  | 2021-05-31 | 2021-06-01 | 2021-06-02 | 2021-06-03 | 2021-06-04 | 2021-06-07 | 2021-06-08 | 2021-06-09 | 2021-06-10 | 2021-06-11 | 2021-06-14 | 2021-06-15 | 2021-06-16 | 2021-06-17 | 2021-06-18
Project Planning | Project Planning | [15 empty] | SW Cha | M | (Team 5) Project Planning.xslx | bar: 2021-05-31 to 2021-06-03
Funcional Requirement | Function Requirement Analysis | [15 empty] | YJ Lee | M | Preliminary Functional Requirement List | bar: 2021-06-04 to 2021-06-08
| Review | [15 empty] | YK Choi | M | Essential Functional Requirement List | bar: 2021-06-04 to 2021-06-08
Security Requirement | Asset List | [15 empty] | YK Choi | M | Asset List | bar: 2021-06-04 to 2021-06-08
| Threat Modeling | [15 empty] | SJ Lee, YK Choi | M | DFD (.tm file from Microsoft Threat Modeling tool) STRIDE | bar: 2021-06-04 to 2021-06-08
| Risk Assessment | [15 empty] | SW Cha | M | OWASP | bar: 2021-06-04 to 2021-06-08
| Mitigation | [15 empty] | SJ Lee | M | Mitigation Strategies | bar: 2021-06-04 to 2021-06-09
| Review | [15 empty] | All | M | Essential Security Requirement List | bar: 2021-06-07 to 2021-06-10
Development | Client - Main Functionality | [15 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-09
| Client - Security | [15 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Server - Main Functionality | [15 empty] | WL Kang | M | Source Codes | bar: 2021-06-07 to 2021-06-09
| Server - Security | [15 empty] | DH Han | M | Source Codes | bar: 2021-06-09 to 2021-06-11
| Open Source Vulnerability analysis | [15 empty] | DH Han | O | open source vulnerability analysis report | bar: 2021-06-10 to 2021-06-14
| Static Analysis | [15 empty] | WL Kang | O | static analysis report | bar: 2021-06-10 to 2021-06-14
Testing | Function Test | [15 empty] | YJ Lee | M | Function Test Case & Report | bar: 2021-06-14 to 2021-06-16
| Security Test | [15 empty] | YJ Lee | M | Security Test Case & Report | bar: 2021-06-14 to 2021-06-16
3. Role and Responsibility
Category | Item | 2021-05-31: Responsibility
Presentation | Phase 1 Presentation | 2021-05-31: WL Kang
| Phase 2 Presentation | 2021-05-31: YJ Lee
Documentation | Chapter 1. Project Overview | 2021-05-31: SW Cha
| Chapter 2. System Description | 2021-05-31: DH Han
| Chapter 3. Threat Modeling | 2021-05-31: SJ Lee, YK Choi
| Chapter 4. Risk Assessment | 2021-05-31: SW Cha
| Chapter 5. Mitigation | 2021-05-31: SJ Lee
| Chapter 6. Security Requirements | 2021-05-31: YJ Lee
| Chapter 7. Implementation | 2021-05-31: DH Han, WL Kang